## Transition Plan
LMRWD Transition Plan and Tasks
Executive Summary
This Transition Plan provides a clear, phased framework for onboarding and establishing the new Administrator of the Lower Minnesota River Watershed District. The plan spans from April to August 2025 and is organized into three core phases: Onboarding & Orientation (Weeks 1–4), Alignment & Authority Transfer (Weeks 4–8), and Evaluation & Legacy (Weeks 8–12).
Across 16 domain areas—from operations and finance to board governance and community engagement—the plan outlines SMART goals, timelines, and support structures to ensure a seamless leadership transition. Key deliverables include the Personnel Committee and Board approval of public transition events, implementation of performance tracking systems, and delivery of a final Transition Report to the Board.
This document serves both as a tactical roadmap and a permanent governance record of the transition. It is designed to support transparency, accountability, and institutional continuity.
Introduction
This Leadership Transition Plan outlines a structured, phased approach to support the successful onboarding and integration of the new Administrator of the Lower Minnesota River Watershed District (LMRWD). It provides a roadmap to ensure continuity of leadership, institutional knowledge transfer, stakeholder confidence, and long-term operational stability.
The transition is divided into three clearly defined phases:
Phase I: Onboarding & Orientation (Weeks 1–4) – Establishes administrative access, contractual clarity, legal grounding, and essential systems onboarding.
Phase II: Alignment & Authority Transfer (Weeks 4–8) – Moves the Administrator into full operational leadership, relationship-building with stakeholders and counties, and strategic alignment with governance and planning documents.
Phase III: Evaluation & Legacy (Weeks 8–12) – Concludes the transition with final evaluations, institutional documentation, and the complete handoff of responsibilities.
Each phase contains individual sections organized around critical transition domains, such as legal compliance, finance, operations, project oversight, stakeholder engagement, and governance. Each section includes:
A clearly defined objective
A set of priority and additional SMART goals with deadlines
Built-in feedback loops and accountability milestones
This plan is both a strategic leadership tool and a practical operations guide. It reflects the District’s commitment to transparency, responsibility, and continuity, and is designed to serve as a reference not only for this transition, but for future leadership handovers. Through intentional coordination, this plan will help ensure that Will, the incoming Administrator, is positioned to lead confidently, capably, and in alignment with the District’s mission and values.
Phase I: Onboarding & Orientation (Weeks 1–4)
Phase I lays the administrative and operational foundation for a successful leadership transition. During this period, the focus is on ensuring full onboarding of the new Administrator, transferring essential institutional knowledge, securing access to systems, establishing oversight structures, and mitigating early-stage risks. All tasks in this phase are tied to clearly defined deliverables with deadlines in the first month.
1.1 Contractor Onboarding Checklist
Objective: Ensure complete and efficient onboarding of the new Administrator, including contract execution, secure access, financial registration, and communication system integration.
1.2 Consultant Role & Scope
Objective: Define a clear, time-limited consulting role for the outgoing Administrator that ensures strategic support without overlapping the authority of the incoming Administrator.
1.3 Legal & Governance
Objective: Ensure the incoming Administrator has the legal knowledge, documentation, and strategic context needed to operate within the statutory and policy framework of the District, and to identify and manage legal risk during the transition.
1.4 Vendor Coordination & Operational Continuity
Objective: Ensure that all contracted vendors experience a smooth and confident transition in leadership, understand updated communication and oversight expectations, and maintain uninterrupted operations.
1.5 Infrastructure & Information Management
Objective: Ensure full operational continuity through a comprehensive review of physical and digital infrastructure, successful knowledge transfer, secure access to systems, and compliant document management.
1.6 Transition Risk Management & Contingency Planning
Objective: Proactively identify, evaluate, and prepare for risks that could impact the success of the leadership transition by implementing clear escalation protocols, actionable contingency.
1.7 Regulatory Compliance & Permitting Oversight
Objective: Ensure uninterrupted oversight of permitting, rule enforcement, and compliance reporting responsibilities during the leadership transition, with a clear understanding of legal responsibilities, workflows, and inter-agency coordination.
Phase II: Alignment & Authority Transfer (Weeks 4–8)
Phase II focuses on the Administrator’s transition from onboarding to active leadership. During this period, Will takes full responsibility for daily operations, staff/vendor coordination, strategic relationships, and governance visibility, while also initiating long-term planning efforts. Key deliverables include mastering operational systems, formalizing partner engagement, preparing for the May Personnel Committee and Board meetings, and publicly affirming Will’s leadership role. The phase builds toward sustained confidence from the Board, counties, partners, and the community.
By the end of Phase II, the following measurable objectives will be completed:
2.1 Operational Management
Objective: Ensure the Administrator has a full understanding of day-to-day operations, vendor relationships (especially with Young Environmental), and performance expectations to support seamless administration and identify opportunities for improvement.
2.2 Financial Administration
Objective: Establish full operational and strategic control over the District’s financial systems, reporting responsibilities, and vendor relationships while ensuring a smooth transfer of signatory authority and institutional knowledge.
2.3 Strategic Planning Alignment
Objective: Ensure the Administrator understands the District’s long-term vision, aligns current operations with the 2018–2027 Watershed Management Plan (WMP), and builds capacity to manage regulatory relationships and funding expectations with BWSR.
2.4 Watershed Management Plan (WMP) Implementation & Update
Objective: Ensure active alignment between District operations and the 2018–2027 Watershed Management Plan, assess progress to date, and prepare for the next WMP update in compliance with BWSR requirements.
2.5 Board Relations & Governance
Objective: Build strong, informed relationships with the Board of Managers, develop fluency in board operations and culture, and assume responsibility for agenda development, meeting logistics, and governance communications.
2.6 Personnel Committee and May Board Meeting Milestones
Objective: Prepare for and successfully facilitate the May 7 Personnel Committee meeting and the May Board meeting, ensuring full compliance with Open Meeting Law, clear communication of transition progress, and approval of key leadership events.
2.7 County Relations
Objective: Establish strong working relationships with each county’s appointed representative and staff liaison, develop a clear understanding of county-level priorities and concerns, and set the foundation for ongoing collaboration, trust, and shared strategic direction.
2.8 Training and Development
Objective: Support the Administrator’s effectiveness by identifying and completing relevant training opportunities in watershed governance, operations, financial management, and public leadership, while integrating learning into real-time responsibilities.
2.9 Key Partners & External Stakeholders
Objective: Build trust and momentum with current partner organizations by initiating personal engagement, clarifying shared responsibilities, and ensuring a seamless leadership handoff that supports collaborative continuity and growth.
2.10 Public Affairs & Communications
Objective: Lead coordinated, professional public communication and event planning efforts around the leadership transition, leveraging the lobbying firm and past messaging to ensure smooth continuity, strong visibility, and community engagement.
2.11 Community Engagement
Objective: Establish a visible, trusted leadership presence within the community by building relationships with key local stakeholders, understanding historical dynamics, and launching a forward-looking engagement strategy that aligns with District goals and values.
2.12 Relational Authority and Public Messaging
Objective: Ensure a clear, public transition of leadership through coordinated messaging, visible endorsement, and symbolic handoffs that affirm Will’s authority with stakeholders, partners, and the public.
2.13 Watershed Boundary Management & Interagency Coordination
Objective: Build a strong understanding of the District’s current watershed boundary adjustment efforts, coordinate with legal and planning stakeholders, and lead a unified interagency communication strategy to support long-term resolution.
2.14 Education & Outreach Program Management
Objective: Strengthen the District’s education and outreach efforts by assessing current strategies, engaging with the Citizen Advisory Committee, and collaborating with Young Environmental to design impactful public engagement initiatives.
2.15 Environmental Project Continuity & Oversight
Objective: Maintain forward momentum and high standards across active environmental projects by assessing current status, collaborating with technical partners, addressing risks early, and ensuring strong documentation and oversight systems.
2.16 Fen Stewardship & Management
Objective: Ensure the continued protection and restoration of calcareous fens within the LMRWD by coordinating with agency partners, monitoring conservation efforts, and increasing public and stakeholder awareness of these rare ecosystems.
Phase III: Evaluation & Legacy (Weeks 8–12)
Phase III represents the culmination of the leadership transition. This final stage is focused on assessing progress, capturing institutional knowledge, resolving remaining responsibilities, and preparing the District for long-term continuity. It prioritizes reflection, final reporting, strategic documentation, and reinforcement of Will’s independent leadership role. By the end of this phase, the Administrator will have assumed full operational, strategic, and relational authority. Support structures will taper, while systems for performance monitoring, partner tracking, and institutional learning will be formalized and handed off.
By the conclusion of Phase III, the following measurable objectives will be completed:
3.1 Capital Projects & Grant Continuity
Objective: Maintain seamless oversight of capital improvement projects and grant-funded initiatives by documenting key timelines, deliverables, and responsibilities, ensuring no disruptions to reporting, compliance, or partner coordination.
3.2 Performance Metrics and Evaluation
Objective: Define, track, and report on meaningful performance indicators to evaluate the success of the leadership transition, identify improvement areas, and establish a foundation for long-term measurement and accountability.
3.3 Final Transition Review
Objective: Deliver a comprehensive evaluation of the transition process, incorporating feedback, performance metrics, and lessons learned into a final report that supports institutional continuity, transparency, and ongoing improvement.
3.4 Outgoing Admin Feedback and Relationship
Objective: Preserve institutional knowledge and strategic insights by documenting reflections from the outgoing Administrator and conducting a structured debrief conversation that supports the long-term success of the incoming leadership.

## May-Aug 2025
Goal | Who | Target Date | Section | Status | Date invoiced | Link | Priority Level
Finalize and submit the executed contract, insurance, business license, and tax ID documentation to administrative records | Microsoft | 2025-05-06 | 1.1 | Completed |  |  | Primary
Complete financial system onboarding, including entry into the payment system and a successful test transaction | CPA | 2025-05-07 | 1.1 |  |  |  | Primary
Deliver secure system login credentials, shared drive access, and calendar invitations | Microsoft | 2025-05-07 | 1.1 | Completed |  |  | Primary
Create listserves for the board, CAC, TAC, etc | Will | 2025-05-08 | 1.1 |  |  |  | Secondary
Schedule and conduct the administrative orientation session to cover all systems and expectations | Chair, Linda | 2025-05-08 | 1.1 | In- Progress |  |  | Primary
Confirm Will is added to all internal communication lists, board directories, and distribution groups |  | 2025-05-13 | 1.1 | In- Progress |  |  | Secondary
Ensure all contract documentation is properly archived in both physical and digital storage systems |  | 2025-05-13 | 1.1 | In- Progress |  |  | Primary
Verify successful login and data access to required platforms (board portal, financial reports, communications systems) |  | 2025-05-15 | 1.1 |  |  |  | Primary
Establish administrative check-in process to resolve onboarding-related issues during Weeks 2–3 |  | 2025-05-15 | 1.1 |  |  |  | Secondary
Establish a shared digital folder for consultant deliverables and access |  | 2025-05-12 | 1.2 |  |  |  | Secondary
Provide Linda with a standardized reporting template for weekly updates |  | 2025-05-13 | 1.2 |  |  |  | Secondary
Approve a written scope of work outlining Linda’s role, deliverables, availability, and hour limits |  | 2025-05-14 | 1.2 |  |  |  | Primary
Confirm Linda’s weekly availability schedule and integrate into a shared calendar |  | 2025-05-15 | 1.2 |  |  |  | Secondary
Complete Board approval of the consultant role and boundaries at the May Personnel Committee Meeting |  | 2025-05-16 | 1.2 |  |  |  | Primary
Identify and document areas where Will holds sole authority to prevent role confusion |  | 2025-05-16 | 1.2 |  |  |  | Primary
Finalize and document a conflict resolution protocol between Linda and Will |  | 2025-05-21 | 1.2 |  |  |  | Secondary
Schedule and conduct an onboarding meeting with legal counsel to review statutes, open meeting law, and contract authorities | Legal | 2025-05-02 | 1.3 | In- Progress |  |  | Primary
Review insurance and indemnification clauses tied to the Administrator's duties and clarify associated responsibilities | Legal | 2025-05-09 | 1.3 |  |  |  | Primary
Review the enabling legislation, Joint Powers Agreement, and board bylaws, and submit a 1-page summary memo to the Board Chair |  | 2025-05-12 | 1.3 |  |  |  | Secondary
Identify and summarize unresolved legal issues or required legal filings in coordination with Linda and legal counsel |  | 2025-05-14 | 1.3 |  |  |  | Secondary
Provide historical context on prior governance disputes or compliance events |  | 2025-05-14 | 1.3 |  |  |  | Secondary
Compile and archive any legacy documentation, case notes, or guidance memos from past transitions or advisory opinions |  | 2025-05-21 | 1.3 |  |  |  | Secondary
Complete review of all vendor contracts, scopes of work, and historical context—including key relationships and sensitivities |  | 2025-05-14 | 1.4 |  |  |  | Primary
Review and edit all vendor-facing communication drafts collaboratively |  | 2025-05-16 | 1.4 |  |  |  | Secondary
Notify vendors of the leadership transition and Will’s role as the primary contact, and send welcome messages |  | 2025-05-19 | 1.4 | In- Progress |  |  | Primary
Identify and document outstanding deliverables, risks, or transition-sensitive tasks |  | 2025-05-21 | 1.4 |  |  |  | Secondary
Schedule and hold orientation meetings with each vendor to review expectations, reporting protocols, and next steps |  | 2025-05-27 | 1.4 | In- Progress |  |  | Primary
Attend at least three vendor onboarding meetings jointly (Will & Linda) |  | 2025-05-27 | 1.4 | 1/3 (YECG |  |  | Primary
Establish and share a centralized vendor reporting and invoicing calendar with all parties |  | 2025-06-02 | 1.4 |  |  |  | Secondary
Confirm successful handoff of oversight responsibilities and update all vendor tracking tools |  | 2025-06-06 | 1.4 |  |  |  | Primary
Deliver a digital access spreadsheet, retention policy overview, and shared folder structure documentation | Microsoft | 2025-05-06 | 1.5 |  |  |  | Secondary
Complete and share a “Handover Log” of all critical records—including permits, vendor data, and institutional documents—with Joseph and Linda |  | 2025-05-28 | 1.5 |  |  |  | Primary
Finalize secure access transfers for email, shared drives, financial platforms, and cloud systems |  | 2025-05-30 | 1.5 | In- Progress |  |  | Primary
Conduct and archive at least two joint procedural walkthroughs of key systems with Linda |  | 2025-06-02 | 1.5 |  |  |  | Secondary
Schedule and conduct a risk identification meeting with Will and Linda | Linda | 2025-05-06 | 1.6 |  |  |  | Secondary
Submit written risk area insights from all team members | ALL | 2025-05-07 | 1.6 |  |  |  | Secondary
Publish a categorized draft list of high-risk areas and potential impacts—such as gaps in access, vendor continuity, or unexecuted contracts | YE | 2025-05-09 | 1.6 |  |  |  | Secondary
Review the LMRWD Rules and administrative procedures, including permit workflows |  | 2025-05-19 | 1.7 |  |  |  | Primary
Meet with legal counsel and engineering team to clarify rule enforcement protocols, delegated responsibilities, and permitting roles |  | 2025-05-23 | 1.7 |  |  |  | Primary
Obtain and review the complete list of open permits, recent applications, and pending enforcement actions |  | 2025-05-23 | 1.7 | In- Progress |  |  | Primary
Map out internal workflows for permit review and approval, including responsible parties for inspections and approvals |  | 2025-05-28 | 1.7 |  |  |  | Primary
Submit a permitting and compliance transition summary memo—including current responsibilities, deadlines, and workflows |  | 2025-05-29 | 1.7 |  |  |  | Secondary
Identify and calendar upcoming regulatory reporting deadlines (BWSR, MPCA, audit cycles) |  | 2025-06-02 | 1.7 | In- Progress |  |  | Primary
Ensure awareness of coordination needs related to MS4/NPDES if applicable, and flag unresolved compliance areas |  | 2025-06-02 | 1.7 |  |  |  | Primary
Confirm key regulatory contacts and reporting coordination points with BWSR, MPCA, and any MS4/NPDES entities |  | 2025-06-02 | 1.7 |  |  |  | Primary
Provide sample reporting tools, milestone trackers, and archived communications to support onboarding | Microsoft | 2025-05-07 | 2.1 |  |  |  | Secondary
Schedule and conduct an onboarding meeting with Young Environmental and facilitate vendor introductions | YE | 2025-05-08 | 2.1 | In- Progress |  |  | Primary
Submit an operational summary memo outlining expectations, workflows, and initial performance observations |  | 2025-05-12 | 2.1 |  |  |  | Secondary
2.1
Physical ID for Will going onsite: business cards, car magnet, car flashing light, hardhat, vest |  | 2025-05-13 | 2.1
Identify at least two operational gaps or process improvement opportunities and document proposed changes |  | 2025-05-14 | 2.1 | In- Progress |  |  | Secondary
Meet with the bookkeeping vendor and complete knowledge transfer on workflows, reporting cadence, and current performance | CPA | 2025-05-02 | 2.2 | In- Progress |  |  | Primary
Complete review of financial systems, including chart of accounts, historical reports, audit materials, and current budget | CPA | 2025-05-06 | 2.2 | In- Progress |  |  | Primary
Walk through monthly and quarterly financial processes, including internal reviews and board prep | CPA | 2025-05-06 | 2.2 | In- Progress |  |  | Primary
Submit a financial transition memo outlining current financial standing, outstanding issues, and next steps | Linda | 2025-05-08 | 2.2 | In- Progress |  |  | Secondary
Transfer signatory authority for all financial accounts | Linda | 2025-05-12 | 2.2 | In- Progress |  |  | Primary
Confirm and document timelines and deliverables for audit preparation, grant reporting, and state reporting |  | 2025-05-12 | 2.2 |  |  |  | Primary
Upload prior-year budgets, amendments, and audit responses to the shared folder |  | 2025-05-13 | 2.2 |  |  |  | Secondary
Identify and document unresolved payments, discrepancies, or friction points in the financial system |  | 2025-05-14 | 2.2 |  |  |  | Secondary
Deliver historical summary of strategic priorities, key implementation milestones, and past board decisions | Linda | 2025-05-06 | 2.3 | In- Progress |  |  | Secondary
Conduct meeting with BWSR to review responsibilities, funding mechanisms, and performance expectations |  | 2025-05-12 | 2.3 |  |  |  | Primary
Map all active projects and vendor activities against WMP goals |  | 2025-05-19 | 2.3 | In- Progress |  |  | Secondary
Identify historical implementation gaps or overperforming areas and recommend future BWSR engagement strategies |  | 2025-05-19 | 2.3 |  |  |  | Secondary
Prepare a briefing on BWSR’s review criteria and expectations for inclusion in the June board packet |  | 2025-05-23 | 2.3 |  |  |  | Secondary
Review the existing WMP, focusing on core goal areas including wetlands, groundwater, floodplain, erosion, stormwater, and bluff protection |  | 2025-06-10 | 2.4 | In- Progress |  |  | Primary
Assess implementation progress and identify gaps or priorities requiring course correction as part of the planning update |  | 2025-06-11 | 2.4 | In- Progress |  |  | Secondary
Confirm ongoing weekly check-in meetings with the Board Chair scheduled through July | Chair | 2025-05-05 | 2.5 | Completed | 2025-05-05 |  | Primary
Walk through the full board packet development process—including collaboration, deadlines, and templates | Linda | 2025-05-09 | 2.5 | In- Progress |  |  | Primary
Complete one-on-one meetings with all five Board members and receive contextual introductions and background notes from Linda | Will | 2025-05-12 | 2.5 |  |  |  | Primary
Watch previous board meeting recordings to understand tone, recurring issues, and governance structure |  | 2025-05-14 | 2.5 |  |  |  | Primary
Receive coaching from Linda on tone, formality, and logistics of board meetings, including A/V needs and presentation roles |  | 2025-05-14 | 2.5 | In- Progress |  |  | Primary
Establish a shared calendar with key board deadlines, reporting tasks, and packet timelines |  | 2025-05-19 | 2.5 |  |  |  | Secondary
Post a legally compliant Personnel Committee meeting notice | Website | 2025-05-12 | 2.6 | In- Progress |  |  | Primary
Submit the draft agenda and all transition plan and event proposal materials for Personnel Committee review | Will | 2025-05-12 | 2.6 |  |  |  | Primary
Identify and prepare responses to likely questions from Board or Committee members |  | 2025-05-14 | 2.6 |  |  |  | Secondary
Present the transition plan at the May Personnel Committee meeting |  | 2025-05-15 | 2.6 |  |  |  | Primary
Finalize and submit updated transition materials and event proposals for the full Board packet |  | 2025-05-22 | 2.6 |  |  |  | Primary
Review and confirm clarity and formatting of the final Board packet materials |  | 2025-05-22 | 2.6 |  |  |  | Primary
Present final proposals and request formal Board approval at the May Board meeting on May |  | 2025-05-23 | 2.6 |  |  |  | Primary
Share a template for county briefing materials and introductory emails |  | 2025-05-15 | 2.7 |  |  |  | Primary
Receive historical context from Linda and Joseph on past challenges, successes, and political dynamics with each county |  | 2025-05-19 | 2.7 | In- Progress |  |  | Primary
Coordinate calendar invitations and logistics for all county meetings |  | 2025-05-23 | 2.7 |  |  |  | Primary
Prepare and deliver a short briefing packet for each meeting, tailored to each county’s priorities and relevant projects |  | 2025-05-28 | 2.7 |  |  |  | Secondary
Establish a shared contact list and communication log for all county liaisons and related staff |  | 2025-06-02 | 2.7 |  |  |  | Secondary
Schedule and conduct introductory meetings with appointed liaisons and lead staff from Dakota, Carver, Scott, and Hennepin Counties |  | 2025-06-17 | 2.7 | In- Progress |  |  | Secondary
Identify at least one opportunity for collaborative engagement or communication improvement with each county |  | 2025-06-27 | 2.7 |  |  |  | Secondary
Receive list of past-recommended trainings and shared internal materials from Linda |  | 2025-05-14 | 2.8 | In- Progress |  |  | Primary
Receive insight from Linda on top three most impactful external trainings |  | 2025-05-16 | 2.8 |  |  |  | Primary
Register for at least one formal external training opportunity (e.g., BWSR, MAWD, AMC) |  | 2025-05-19 | 2.8 |  |  |  | Primary
Hold a 1:1 coaching session with Linda to reflect on development goals and transition priorities |  | 2025-05-23 | 2.8 | In- Progress |  |  | Primary
Launch a professional development log |  | 2025-05-28 | 2.8 |  |  |  | Secondary
Schedule and complete at least two additional learning opportunities (internal or external) |  | 2025-08-22 | 2.8 |  |  |  | Secondary
Identify at least one long-term leadership program or certification path for future consideration |  | 2025-07-01 | 2.8 |  |  |  | Secondary
Obtain and review the full list of key partners, including MOUs, scopes of work, and relationship history |  | 2025-05-14 | 2.9 |  |  |  | Primary
Identify and begin outreach to the top 10 strategic priority partners |  | 2025-05-16 | 2.9 |  |  |  | Primary
Make personal introductions for the highest-priority partners |  | 2025-07-19 | 2.9 |  |  |  | Primary
Complete an introductory meeting with the public affairs/lobbying firm |  | 2025-05-02 | 2.10 |  |  |  | Primary
Draft press releases and event concepts for both Linda’s Retirement Event and Will’s Welcome Event |  | 2025-05-03 | 2.10 |  |  |  | Secondary
Present the complete event and press strategy to the Personnel Committee |  | 2025-05-04 | 2.10 |  |  |  | Secondary
Finalize materials for the May Board packet |  | 2025-05-05 | 2.10 |  |  |  | Secondary
Begin implementation of event logistics, including venue confirmation and stakeholder outreach |  | 2025-05-06 | 2.10 |  |  |  | Secondary
Identify top 10 priority invitees for each event and send initial outreach messages |  | 2025-05-07 | 2.10 |  |  |  | Secondary
Receive 3–5 sample press releases, invitations, or messaging templates from Linda |  | 2025-05-08 | 2.10 |  |  |  | Secondary
Provide or confirm speaker and co-host contact info, with recommendations |  | 2025-05-09 | 2.10 |  |  |  | Secondary
Attend at least one planning meeting for each event |  | 2025-05-10 | 2.10 |  |  |  | Secondary
Complete review of historical community engagement records and receive stakeholder contact list |  | 2025-05-12 | 2. 11 |  |  |  | Primary
Publish an introductory message to community partners |  | 2025-05-14 | 2.11 |  |  |  | Primary
Attend a minimum of three community meetings or events |  | 2025-05-15 | 2.11 |  |  |  | Primary
Attend at least one community meeting jointly with Linda |  | 2025-05-16 | 2.11 |  |  |  | Primary
Facilitate introductions to top five stakeholder leaders |  | 2025-05-18 | 2.11 |  |  |  | Primary
Recommend at least two priority events or forums to attend |  | 2025-05-20 | 2.11 | In- Progress |  |  | Secondary
Draft and approve shared transition messaging with Linda |  | 2025-05-21 | 2.12 |  |  |  | Primary
Identify and schedule at least three symbolic handoff moments |  | 2025-05-22 | 2.12 |  |  |  | Primary
Schedule and complete a joint public appearance with Linda and Joseph |  | 2025-05-23 | 2.12 |  |  |  | Secondary
Distribute press release via email and web |  | 2025-05-25 | 2.12 |  |  |  | Primary
Ensure public-facing platforms reflect Will’s leadership role |  | 2025-05-26 | 2.12 |  |  |  | Primary
Review final communications across platforms for tone and consistency |  | 2025-05-27 | 2.12 |  |  |  | Primary
Review all boundaries, legal background, and GIS data |  | 2025-05-28 | 2.13 | In- Progress |  |  | Primary
Reach out to water planners in region |  | 2025-05-31 | 2.13 |  |  |  | Primary
Submit boundary coordination summary memo |  | 2025-06-01 | 2.13 |  |  |  | Secondary
Complete a review of current education and outreach plans |  | 2025-06-03 | 2.14 |  |  |  | Primary
Attend a Citizen Advisory Committee (CAC) meeting |  | 2025-06-04 | 2.14 | Completed |  |  | Primary
Propose two outreach initiatives in collaboration with Young Environmental |  | 2025-06-06 | 2.14 |  |  |  | Secondary
Conduct stakeholder project status meetings |  | 2025-06-07 | 2.15 |  |  |  | Primary
Implement comprehensive project tracking system |  | 2025-06-08 | 2.15 |  |  |  | Secondary
Identify risks and implement mitigation strategies |  | 2025-06-09 | 2.15 | In- Progress |  |  | Primary
Ensure all project documentation is current and archived |  | 2025-06-10 | 2.15 |  |  |  | Primary
Review existing fen stewardship plans and data |  | 2025-06-11 | 2.16 | In- Progress |  |  | Primary
Hold status meeting with MnDNR and consultants |  | 2025-06-12 | 2.16 |  |  |  | Primary
Identify 3 key risks and propose corrective actions |  | 2025-06-13 | 2.16 |  |  |  | Secondary
Review the full CIP master list, including schedules, scopes, and funding sources |  | 2025-05-10 | 3.1 |  |  |  | Primary
Meet with engineering consultants and grant managers to review fiscal milestones and project status |  | 2025-05-13 | 3.1 | In- Progress |  |  | Primary
Create a detailed tracking system for all active grants |  | 2025-05-17 | 3.1 |  |  |  | Secondary
Identify and resolve any pending reimbursement submissions |  | 2025-05-30 | 3.1 |  |  |  | Primary
Ensure access to all grant reporting portals and systems |  | 2025-05-15 | 3.1 |  |  |  | Primary
Archive grant documentation and tracking tools |  | 2025-06-03 | 3.1 |  |  |  | Secondary
Begin weekly tracking and progress reviews |  | 2025-05-10 | 3.2 |  |  |  | Primary
Recommend 1–2 benchmarks to guide KPI targets |  | 2025-05-10 | 3.2 |  |  |  | Secondary
Participate in KPI review session with Joseph and Linda |  | Week of June 10 | 3.2 |  |  |  | Secondary
Flag 2–3 KPIs for long-term adoption |  | 2025-07-15 | 3.2 |  |  |  | Secondary
Prepare slides or talking points for July Board meeting |  | 2025-07-14 | 3.3 |  |  |  | Primary
Deliver verbal presentation at July Board meeting |  | 2025-07-15 | 3.3 |  |  |  | Primary
Receive consultant feedback from Linda |  | 2025-07-12 | 3.3 |  |  |  | Primary
Identify and address unresolved documentation issues |  | 2025-07-11 | 3.3 |  |  |  | Primary

## Sept-Dec 2025
Goal | Who | Due Date | Section | Status | Date invoiced | Link | Priority Level
Complete an inventory of physical storage, identify high-value items for digitization, and organize scanning priorities |  | 45796 | 1.5 |  |  |  | Next workplan
Evaluate the District’s office space (including lease, cost, and function) and submit a summary of findings |  | 45797 | 1.5 |  |  |  | Next workplan
Review the document retention policy (with historical notes from Linda) and propose a digitization plan for critical files |  | 45800 | 1.5 |  |  |  | Next workplan
Confirm archival structures and set up long-term digital storage systems in compliance with retention rules |  | 45804 | 1.5 | In- Progress |  |  | Next workplan
Migrate domain, webhosting, and emails to be owned by the District and utilize Microsoft 365 | [6 empty] | Next workplan
Submit a final infrastructure and records transition memo to the Board |  | 45825 | 1.5 |  |  |  | Next workplan
Launch digitization of priority files |  | 45830 | 1.5 |  |  |  | Next workplan
Complete setup of storage systems |  | 45830 | 1.5 |  |  |  | Next workplan
Identify and document at least two historical transition or operational risks that impacted the District |  | 45791 | 1.6 |  |  |  | Next workplan
Identify at least three actionable fallback strategies to address critical risks or delays |  | 45791 | 1.6 |  |  |  | Next workplan
Participate in a final review and planning session to finalize fallback strategies |  | 45791 | 1.6 |  |  |  | Next workplan
Confirm readiness to implement fallback actions, and ensure alignment with District policies and open meeting requirements |  | 45796 | 1.6 |  |  |  | Next workplan
Update and circulate a revised risk and contingency plan if needed, based on emerging issues |  | 45800 | 1.6 |  |  |  | Next workplan
Document recent rule revisions or administrative changes with legal counsel and archive guidance for future use |  | 45810 | 1.7 |  |  |  | Next workplan
Complete review of both components of the Young Environmental contract and provide a written in-scope vs. out-of-scope summary to Joseph and Linda | YE | 45783 | 2.1 | In- Progress |  |  | Next workplan
Review and recommend updates to vendor tracking systems and reporting workflows |  | 45796 | 2.1 |  |  |  | Next workplan
Develop a detailed WMP update project plan in collaboration with Young Environmental, including timeline, stakeholder roles, and required data collection |  | 45845 | 2.4 |  |  |  | Next workplan
Initiate stakeholder engagement activities, including public outreach or advisory input |  | 45839 | 2.4 |  |  |  | Next workplan
Submit a preliminary update framework and BWSR engagement plan |  | 45884 | 2.4 |  |  |  | Next workplan
Create visual contact map of relevant agencies